## Slide 1
Yes it is Possible to Accredit 18 One Analyst Digital Evidence Laboratories
Rhesa G. Gilliland, Assistant Laboratory Director

## Slide 2: Forensic Laboratory Services (FLS)
FLS become responsible for the 18 DEU laboratories in early 2011
Laboratory Director looked for an experienced ISO accreditation manager.
Enter on board October 2011

## Slide 3
Background
Laboratory Director of a ISO accredited Digital Evidence Laboratory for 4+ years
Directly involved in two rounds of ISO accreditations of the Computer Forensic area
Involved with Digital Evidence since 1997

## Slide 4: Situation
Status
  21 Analysts – 18 locations
    Embedded in local division offices
  Main laboratory legacy accredited
  New management (two direct reports managing the 21 analysts)
  Minimal policy and procedures
  Deadline of 2014 to join the main lab going for ISO

## Slide 5: Where to start?
Figure out what existing practices are
Fix immediate issues
  Technical reviews and Admin reviews
  Commence policy writing
    Create policy to align with ISO 17025 and any supplemental requirements
  Dealing with distance
    How were we going to do tech reviews?
    Determining what is evidence

## Slide 6: Where to start?
Meetings, meetings, meetings
On-site visits
Records management
Competency Testing
Training Manual

## Slide 7: Where to start?
Explain why over and over and over again
  Why are we doing this?
  We were fine before!
  This is taking me away from my casework!
Security
  Buy in from local management/law enforcement to create an island of control in their location
  Do you want to be in the Chain of Custody?

## Slide 8: Where to start?
Equipment
  Getting a handle on what is considered critical
    Policy says…..
    Develop test plans and how to keep the records
Software
  What needs to be validated (verified)?
    What do we have?
    Valid licensed copies?
    Creating a list

## Slide 9: Struggles
Employee buy-in
Constant changing of policy and procedures
  Try out something – If it doesn’t work change it
Reinforcement of process
  All management must be on the same page
Interpreting what policy means!
  Overthinking and adding more requirements unintentionally

## Slide 10: Lessons Learned
Use other’s policy and procedures who have gone through this and tweak to fit your organization
Finding balance
  Rapid policy deployment
  Effective change
More site visits by Laboratory Director/Quality Assurance Manager

## Slide 11: Questions?
Rhesa G. Gilliland
Assistant Laboratory Director
USPIS Forensic Laboratory Services
22433 Randolph Drive, Dulles, VA 20104-1000
W – 703-406-7150
C – 240-506-3757